Watermark Town Initiative workshop Saturday 13th June 2026

Bradley Stoke Town Council is working towards becoming a Watermark Town, as part of the Town’s Council’s Local Climate and Nature Action Plan. Three topic areas were considered: Waste Water and Drinking Water. The Sustainability element will be woven into the two topic areas.

The third workshop was held on Saturday 13th June 2026 and attended by Councillors Sue Bandcroft and Jenny James, BSTC staff Sharon Petela, Phil Francis-Barber, Raphaela Boghi and Gillian Allen, Sara Messenger (representing Bradley Stoke in Bloom, Green Gym and the Three Brooks Nature Conservation Group) and Mark Manning, a resident who works for Sustainable Drainage Solutions. Apologies received from Councillors Natalie Field and Jon Williams.

| Waste Water |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Initiative | Comments | Priority | Resources Required | Timescale | Lead on Project | Notes & Actions |  |
| 1 | Cleaning wipes, wet wipes, tanning wipes – education on correct disposal | Would involve engaging with nurseries, Mamas, pre-schools and involve education with parents. These cause 90% of sewer blockages. Campaign resources available from Wessex Water. Fine to Flush Certification Scheme - to explore options and implement accordingly with BSTC leading by example. | First phase as it would be a quick win/campaign to do. | Explore obtaining the Fine To Flush certification (Water Research Council) for the Town Council and then involve pre-schools, nurseries, Mamas Bristol etc. Include as part of article in next BSTC newsletter. Produce social media video to promote messages | 3-4 months | BSTC | BSTC to design a poster and education campaign for website, social media and forthcoming newsletter |  |
| 2 | 3 P’s campaign (Paper, Pee, Poo). | Campaign resources possibly available from Wessex Water. | First phase as can be a quick campaign to do | Combine with 1 (wipes etc.) as part of education campaign and include in BSTC newsletter article | 3-4 months | BSTC | BSTC to design a poster and education campaign for website, social media and forthcoming newsletter |  |
| 3 | Disposal of cooking oils, fats | Education campaign. Campaign resources available from Wessex Water. | First phase as it would be a quick win/campaign to do. | Wessex Water have been approached for available resources to include in next BSTC newsletter and add to website. | 3-4 months | BSTC/Wessex Water | BSTC to design a poster and education campaign for website, social media and forthcoming newsletter |  |
| 4 | Shower times & 4-minute song | ? timers available via Wessex water. Education campaign. Campaign resources available from Wessex Water. Households can order from Bristol Water or Wessex Water timers depending on which company supplies their water | First phase as can be a quick campaign to do | Wessex Water have been approached for available resources to include in next BSTC newsletter and add to website. | 3-4 months | BSTC/Wessex Water | BSTC to design a poster and education campaign for website, social media and forthcoming newsletter |  |
|  | Initiative | Comments | Priority | Resources Required | Timescale | Lead on Project | Notes & Actions |  |
| 5 | De-urbanising gardens & driveways [more soakaways] | Green drainage features e.g. porous surfaces with planted areas. Retrofitting sustainable urban drainage schemes where funding permits (e.g. rain gardens). | First phase as can be a quick campaign to do | Identify options and possible sites. Encourage private households. | 3-4 months | BSTC | BSTC to source a poster for an "Ideal Front Garden" to be included as part of the education project |  |
| 6 | Only Rain Down The Drain Campaign | Three schools have artwork. ? expand to some other schools if funding is granted. | Third phase | More costs effective option would be to undertake Yellow Fish campaign. Purchase yellow chalk paint and stencils, liaise with school to publicise (target school eco-councils). Start with BSTC sites. | 3-4 months | BSTC/BS Green Gym | BSTC to send emails to schools + local businesses and to work with Green Gym - aim for family initiative (small campaign). BSTC to purchase yellow chalk paint. Green Gym to organise stencils |  |
| 7 | Developing rain gardens [gardens storing rainwater] | Would require advice to implement; could learn from other Councils as part of Watermark Towns Network | Second phase | Development of these initially at three BSTC sites. Particularly important in locations where there are bee highways and to encourage wildlife | 6 months | BSTC/SGC | BSTC in contact with SGC as may be potential funding through Resilient Frome - rain management project |  |
| 8 | Pond dipping areas including education | Will be added to the Town map which is being produced by Wessex Water. | Second phase | Look, learn, leave approach is best for pond dipping so that wildlife etc. is not 'stolen' from the ponds | 6 months | Wessex Water | BSTC to contact Wessex Water re. production of the Town Map |  |
| 9 | Naming of ponds that have been created |  | Second phase | Wessex Water to include names on the town map | 6 months | Wessex Water | BSTC to contact Wessex Water re. production of the Town Map |  |
| 10 | Tiny ponds | Could learn from other Councils as part of Watermark Towns Network. Explore project undertaken in Taunton | Summer phase | Contact Wessex Water to ascertain which councils did this campaign and then contact those councils | 6-8 months | BSTC | BSTC to contact Taunton Town Council re. their project |  |
| 11 | Addressing Combined Sewer Overflows discharge into Stoke Brook which flows into ponds | Reducing misconnections and drains with pollution | Second or third phase |  |  |  | Mark has had conversation with Wessex Water CEO regarding local CSOs - this is a strategic issue outside of the direct remit of parish ad town councils, however, need to raise concerns with Wessex Water/MP for them to take direct action |  |
|  | Initiative | Comments | Priority | Resources Required | Timescale | Lead on Project | Notes & Actions |  |
| 12 | Water butts and leaky butts | Slowing the flow of heavy rain |  |  |  |  | Potential future project |  |
| 13 | Upgrades to amenity areas | Provision of solar fountains etc. |  |  |  |  | Potential future project |  |

| Drinking Water |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | Initiative | Comments | Priority |  | Resources Required |  | Timescale |  | Lead on Project | Notes & Actions |  |  |
| 1 | Develop water refill stations in public areas | Develop laminated signs with a tap to show that it is drinking water. Target pubs as well as BSTC sites. | First phase |  | Publicise this facility at BSTC sites |  | 3-4 months |  | BSTC | BSTC to design signs for BSTC sites, also add information to Town Council website within Activity Centres and also on Watermark Town Initiative section |  |  |
| 2 | Have dog water bowls in public areas | Already happens at Council premises. Target pubs as well as BSTC sites. Develop a picture wall of places in Bradley Stoke that have water bowls for dogs. | Second phase |  | Publicise this facility at BSTC sites and consider shallower bowls for wildlife |  | 3-4 months |  | BSTC | BSTC to encourage local businesses etc. to provide dog water bowls, photos to be taken and added to a section on the Town council website under Watermark Town Initiative to create a map of locations. |  |  |
| 3 | Saving the cold water from a running tap whilst waiting for the water to become hot | Design messaging for education campaign | Summer phase: campaign/ education |  | Include in next BSTC newsletter as ideally a summer campaign |  | 3-4 months |  | BSTC | BSTC to design a poster and education campaign for website, social media and forthcoming newsletter |  |  |
| 4 | Toilet cistern – to reduce water usage by having ‘hippo’ | Households can order a water buffalo from Bristol Water to install or water hippo from Wessex Water depending on which company is their provider | Third phase campaign |  | Speak to Wessex Water for provision of resources |  | 3-4 months |  | BSTC/Wessex Water | BSTC to design a poster and education campaign for website, social media and forthcoming newsletter |  |  |
| 5 | Raise awareness of benefits of Smart Meters to households who do not have these | Wessex Water can provide messages. | First phase |  |  |  | 3-4 months |  | BSTC/Wessex Water | BSTC to design a poster and education campaign for website, social media and forthcoming newsletter |  |  |
|  | Initiative | Comments |  | Priority | Resources Required | Timescale |  | Lead on Project |  |  | Notes & Actions |  |
| 6 | Locks on outside taps | Prevents accidental damage or unauthorised usage to outdoor water supplies | First phase |  | Quick fix to prevent excess water usage |  | 3-4 months |  | BSTC | Completed - Locks fitted to outside tap in compound at Jubilee Centre and Baileys Court Activity Centre. Outside tap at book way activity Centre is not publicly accessible as is behind locked gate. |  |  |
| 7 | Water audit | Starting with Council premises/activities to show leading by example. e.g. With Bailey’s Court development has water shutdown facility been included in the design brief. e.g. Bowls & Cricket Club – what time of day does watering occur (When cooler so water does not evaporate). Learn from audits completed by other Watermark Towns | Ongoing |  | Work with SDS to carry out a water audit of Bowls Green watering |  | Ongoing |  | BSTC/SDS | Phil and Mark have met on site at Baileys Court Activity Centre linked to site redevelopment - this is a long-term project |  |  |
| 8 | Rainwater harvesting | Explore options for all new build to reuse rainwater. Learn from network of Watermark Towns |  |  |  |  |  |  |  | Potential future project |  |  |
| 9 | Work with the Housing Association Curo and Woodstock Housing to include water butts at their sites |  |  |  |  |  |  |  |  | Potential future project |  |  |